# Stages

Stage 1 — Prepare the training conditions for Voter 1

Purpose: prepare the three datasets that will be compared when fine-tuning XLM-RoBERTa.
Portfolio reference: Sections 3.3.2 and 3.6.1.

| Stage | Implementation work | Main output |
| --- | --- | --- |
| 1.1 — MESocSentiment preparation: Candidate A | Prepare the original corpus, reserve supplied test matches, remove flagged near-duplicates, scan suspicious text and document handling decisions. | Candidate A dataset, exclusions, quality report and manifest. |
| 1.2 — Expert corpus preparation and partitioning | Validate labels, preserve author IDs, identify the code-mixed portion, separate unlabelled rows and create fixed partitions. | Expert training, development, calibration and secondary-test files; partition manifest. |
| 1.3 — Expert-only preparation: Candidate B | Build Candidate B using only the expert data permitted for Voter 1 training. | Candidate B dataset with documented inclusion rules. |
| 1.4 — Combined preparation: Candidate C | Combine eligible A and B records, remove cross-source duplicates and subsample the majority neutral class using a recorded rule and seed. | Candidate C dataset and sampling log. |
| 1.5 — Cross-dataset checks and training freeze | Check overlap with protected expert partitions, measure tokenizer lengths, settle suspicious-text handling and freeze all three training inputs. | Final A/B/C manifests and shared training configuration. |

The portfolio allocates the 2,281 labelled code-mixed expert posts as follows:

| Partition | Posts | Purpose |
| --- | --- | --- |
| Training | 800 | Voter 1 fine-tuning |
| Held-out development | 600 | Candidate comparison, threshold tuning and pipeline trial |
| Annotator calibration | 120 | Assess annotator readiness |
| Secondary test | 761 | Independent RQ2 evaluation |

Your current position: Stage 1.1 is substantially implemented, with 16,968 candidate posts remaining. Suspicious-text decisions and the later cross-dataset checks still prevent a final training freeze.

Stage 2 — Train and select Voter 1

Purpose: determine which training condition produces the strongest XLM-R voter.
Portfolio reference: Section 3.3.2.

| Stage | Implementation work | Main output |
| --- | --- | --- |
| 2.1 — Environment and model setup | Pin model/tokenizer versions, software versions and seeds; verify memory use on the intended workstation. | Reproducible environment and configuration. |
| 2.2 — Shared training pipeline | Implement tokenisation, training, checkpointing and evaluation with the same hyperparameters across A/B/C. | Reusable training script. |
| 2.3 — Candidate comparison | Train each condition under three seeds: nine runs. Score them on the permitted held-out expert data. | Per-run Macro-F1 and class-level results. |
| 2.4 — Select and freeze Voter 1 | Choose the condition by mean Macro-F1; record the rule used to select its operational checkpoint. Examine predicted neutral prevalence. | Frozen Voter 1 checkpoint and selection report. |

Complete this comparison before producing the machine-labelled target corpus.

Stage 3 — Prepare the target corpus

Purpose: prepare the separate, initially unlabelled Maskat corpus that your framework will annotate.
Portfolio reference: Sections 3.2 and 3.7.3.

| Stage | Implementation work | Main output |
| --- | --- | --- |
| 3.1 — Source inventory and identifiers | Start from the raw file, assign stable post IDs and retain author IDs. | Traceable Tier 1 input. |
| 3.2 — Filtering and light cleaning | Apply documented duplicate, minimum-length and spam rules; handle URLs and mentions while preserving sentiment-bearing features. | Filtered corpus and exclusion log. |
| 3.3 — Analysis attributes | Compute code-mixing measures and define a noisy-spelling indicator for later robustness analysis. | Per-post attributes and documented methods. |
| 3.4 — Corpus validation and freeze | Verify counts, author coverage, text integrity and reproducibility. | Frozen annotation input and manifest. |

This is a different preparation task from Stage 1.1. MESocSentiment trains a candidate voter; the target corpus becomes your project’s annotated resource.

Stage 3 can proceed alongside Stage 2 once shared data-handling rules are settled.

Stage 4 — Build and validate the annotation framework

Purpose: implement the three voters, confidence gate and adjudicator.
Portfolio reference: Sections 3.3–3.6.1 and 3.8.

| Stage | Implementation work | Main output |
| --- | --- | --- |
| 4.1 — Voter inference | Integrate the selected XLM-R, Llama 3.1 8B and Qwen2.5 7B Instruct. Run generative models sequentially as required by memory. | Per-post predictions. |
| 4.2 — Confidence extraction | Store probabilities across negative, neutral and positive for each voter. Verify how label words are tokenised by each generative model. | Cached probability distributions. |
| 4.3 — Confidence gate | Accept a label only when at least two agreeing voters each meet their own threshold. Route everything else to adjudication. | Routing implementation and branch checks. |
| 4.4 — Adjudicator | Integrate the specified SEA-LION model from the Gemma 2 lineage. Supply the text and anonymous votes; retry runtime failures. | Final labels for routed posts. |
| 4.5 — Expert-data validation | Use the 600-post development portion to tune thresholds and assess the complete pipeline, including inherited bias and adjudication performance. | Thresholds, diagnostic results and frozen configuration. |
| 4.6 — Operational readiness | Implement resumable output, completed-ID tracking, checkpoint validation and scheduled release of the shared GPU. | Tested long-run execution system. |

Posts must not be discarded merely because the voters disagree.

Stage 5 — Pilot and produce the annotated corpus

Purpose: generate Tier 2, the main RQ1 dataset.
Portfolio reference: Sections 3.1.2 and 3.8.2.

| Stage | Implementation work | Main output |
| --- | --- | --- |
| 5.1 — Throughput pilot | Process 5,000–10,000 target posts. Measure inference speed, adjudication share, memory and end-to-end runtime. | Measured compute estimate. |
| 5.2 — Final run sizing | Select the largest feasible run within the timetable, respecting the portfolio’s 150,000-post minimum. | Recorded run scope. |
| 5.3 — Full annotation | Run voters, gate and adjudicator with resumable outputs. | Tier 2 labels, probabilities and routes. |
| 5.4 — Output audit | Check missing IDs, duplicate outputs, invalid labels, unresolved failures and route totals. | Verified Tier 2 corpus and production report. |

Stage 6 — Human validation and RQ1 evaluation

Purpose: create Tier 3 and test H1.
Portfolio reference: Sections 3.6.2–3.6.4.

| Stage | Implementation work | Main output |
| --- | --- | --- |
| 6.1 — Annotator preparation and calibration | Finalise guidelines and assess two bilingual annotators against the reserved calibration data before main annotation. | Guidelines and calibration results. |
| 6.2 — Gold-sample selection | Select 500–1,000 posts, accounting for predicted class, routing branch, code-mixing band and author caps. | Frozen sample and sampling record. |
| 6.3 — Independent annotation | Collect sentiment, sarcasm and difficulty judgements while hiding machine labels. | Two independent annotation files. |
| 6.4 — Gold-set finalisation | Measure inter-annotator agreement before discussion, then resolve disagreements by consensus. | Tier 3 gold labels. |
| 6.5 — H1 comparison | Compare framework labels and prescribed baselines against the same gold labels; report agreement and class prevalence. | RQ1 results and error analysis. |
| 6.6 — Sensitivity analysis | Examine threshold changes and stricter routing rules using cached probabilities, rerunning adjudication where needed. | Routing-sensitivity results. |

Annotator recruitment and guideline preparation can start earlier to avoid delaying this stage.

Stage 7 — RQ2 experiments and final release

Purpose: compare multilingual and monolingual classifiers and package the research evidence.
Portfolio reference: Sections 3.7–3.8.

| Stage | Implementation work | Main output |
| --- | --- | --- |
| 7.1 — Author-disjoint experiment design | Prepare five author folds, protect gold evaluation records and prevent expert secondary-test authors from entering training. | Split manifests and leakage checks. |
| 7.2 — Controlled model training | Train separate XLM-R, BERT-base and IndoBERT models on identical permitted data, using at least three seeds. | Independent RQ2 checkpoints. |
| 7.3 — Evaluation | Evaluate held-out gold posts in their corresponding author folds and the protected expert secondary test set. | Macro-F1, per-class results and variation across seeds/folds. |
| 7.4 — Robustness and error analysis | Compare code-mixing bands, noisy-spelling groups, author variation and relevant sarcasm cases. | Evidence addressing H2 and limitations. |
| 7.5 — Reproducibility and write-up | Assemble scripts, configurations, prompts, thresholds, hashes, results and labels keyed to stable IDs. | Final implementation package and results chapters. |

# FYP 2 Implementation and Progress Tracker

Project: Automated Sentiment Annotation and Performance Evaluation of Transformer Models on Highly Code-Mixed Malaysian Social Media Text
Student: Ng Yong Vay
System preview: 6 November 2026
System testing: 20 November 2026
Final submission: To confirm
Last updated: __________

1. Purpose

This document records the implementation steps, completion criteria, evidence, decisions, and progress of FYP 2.

The project has two research components:

- RQ1: Implement and evaluate the automated annotation framework, producing at least 150,000 sentiment-labelled posts.

- RQ2: Compare XLM-RoBERTa, English BERT-base, and IndoBERT using common training data and independent human-labelled evaluation data.

A step is complete only when its completion criteria are satisfied and its evidence location is recorded.

Use these statuses: Not started / In progress / Blocked / Complete.

2. Starting position

- The required datasets have been downloaded.

- The target raw corpus contains 709,012 rows.

- The expert public-security dataset contains 10,000 rows.

- MESocSentiment contains 19,714 rows.

- A shared RTX 2080 SUPER with 8 GB VRAM is available.

- Two bilingual annotators are confirmed.

- Implementation had not started when planning began.

These facts establish availability. Data cleaning, label verification, and leakage checks remain necessary.

3. Implementation checklist

Step 1 — Confirm requirements and scope

Tasks

- Confirm what must be demonstrated at the preview.

- Confirm whether system testing requires completed research results.

- Record the final submission deadline.

- Record available working hours per week.

- Set the cloud-computing budget and confirm workstation access.

- Confirm the experimental commitments with the supervisor.

Complete when: The assessment expectations, available resources, and project scope are recorded.

Evidence: Requirements checklist and supervisor meeting notes.

Status: __________
Actual hours: __________
Evidence location: __________

Step 2 — Set up the project and computing environment

Tasks

- Create folders for code, configurations, data manifests, experiments, results, and documentation.

- Establish version control and backups.

- Prepare the Python environment.

- Record hardware, drivers, libraries, and software versions.

- Record exact model and tokenizer revisions.

- Test loading each required model separately.

- Process sample inputs and record memory usage.

- Verify that saved outputs survive an interrupted session.

Complete when: Every required model role can run in a documented environment, and outputs can be recovered.

Evidence: Environment file, hardware record, model-loading logs, and backup test.

Status: __________
Actual hours: __________
Evidence location: __________

Step 3 — Audit and clean the input datasets

Tasks

- Preserve the original source files unchanged.

- Record dataset origins, versions, checksums, and available usage terms.

- Check columns, missing values, text encoding, and author identifiers.

- Assign stable post IDs before filtering.

- Standardise sentiment-label mappings.

- Identify exact and near-duplicates.

- Inspect short-post and spam-filtering rules.

- Preserve emojis, negation, punctuation, capitalisation, and informal spelling.

- Record retained and removed counts with reasons.

- Check overlap across the different datasets.

Complete when: Prepared records have usable text, stable IDs, documented labels, and traceable preprocessing.

Evidence: Dataset inventory, label dictionary, preprocessing code, filtering report, and duplicate report.

Status: __________
Actual hours: __________
Evidence location: __________

Step 4 — Freeze expert-data partitions

Tasks

- Verify the usable expert-labelled code-mixed records.

- Allocate authors to training, development, calibration, and secondary testing.

- Aim for the proposal’s approximate allocations: 800, 600, 120, and 761 posts.

- Prioritise author separation over exact counts.

- Exclude held-out authors from all expert training subsets, including monolingual records.

- Check prohibited author and content overlap.

- Save post IDs and their assigned partitions.

- Record achieved post counts, author counts, and class distributions.

- Freeze the partition version before model development.

Complete when: Leakage checks pass and subsequent experiments can reuse identical saved assignments.

Evidence: Partition manifests, allocation summary, and leakage-check results.

Status: __________
Actual hours: __________
Evidence location: __________

Step 5 — Train and select the XLM-R annotation voter

Tasks

- Implement three-class sentiment training.

- Prepare the three training conditions specified in the proposal.

- Keep training settings consistent across conditions.

- Run three seeds for each condition: nine runs in total.

- Compare mean development Macro-F1.

- Inspect class-specific errors and prediction distributions.

- Record the selected training condition and deployed-checkpoint selection rule.

- Save the voter, tokenizer, label mapping, and configuration.

Complete when: The voter selection is supported by development evidence and the saved model produces valid class probabilities.

Evidence: Nine-run comparison table, training logs, selection decision, and checkpoint location.

Status: __________
Actual hours: __________
Evidence location: __________

Step 6 — Implement Llama and Qwen voters

Tasks

- Prepare common sentiment instructions.

- Apply each model’s correct chat template.

- Verify label tokenisation in the actual answer context.

- Implement the appropriate label-probability calculation.

- Check that probabilities are valid and sum to one.

- Record model, prompt, quantisation, and decoding versions.

- Save all three label probabilities and predicted labels for each post.

Complete when: Both voters produce correctly calculated, traceable outputs. Confidence is obtained from model scores rather than generated as a verbal percentage.

Evidence: Prompt files, tokenisation checks, confidence-calculation tests, and sample prediction records.

Status: __________
Actual hours: __________
Evidence location: __________

Step 7 — Implement routing and adjudication

Tasks

- Join voter outputs using stable post IDs.

- Accept a label only when two agreeing voters each meet their own threshold.

- Route every other case to SEA-LION.

- Provide anonymous voter labels to the adjudicator.

- Validate the final sentiment output.

- Record runtime failures and implement retries.

- Save original votes, probabilities, routing reasons, and final labels.

- Test all routing patterns, including weak unanimity and three-way disagreement.

Complete when: Routing matches the proposal and unresolved processing failures remain visible rather than silently dropping posts.

Evidence: Routing tests, adjudication prompt, output schema, and failure logs.

Status: __________
Actual hours: __________
Evidence location: __________

Step 8 — Validate the pipeline and run the pilot

Tasks

- Define threshold-selection criteria and tie-breaking rules.

- Tune only on permitted development data.

- Inspect annotation quality and adjudication corrections/errors.

- Run a small component test.

- Run an integration test and deliberately interrupt it.

- Verify correct resumption without missing or duplicate outputs.

- Run the 5,000–10,000-post throughput pilot.

- Measure throughput, memory, loading time, retries, and adjudication rate.

- Forecast full processing time and cost.

- Freeze the selected annotation configuration.

Complete when: The pipeline works reliably, its workload is measured, and the selected configuration can be reproduced.

Evidence: Development results, pilot report, recovery test, runtime forecast, and configuration manifest.

Status: __________
Actual hours: __________
Evidence location: __________

Step 9 — Produce the machine-labelled corpus

Tasks

- Execute all three voters using the frozen configuration.

- Apply routing and adjudicate the required posts.

- Save resumable output batches.

- Investigate and retry failed records.

- Check unique IDs, valid labels, complete probabilities, and routing consistency.

- Confirm at least 150,000 successfully annotated eligible posts.

- Record class distribution, author coverage, routing proportions, and runtime.

- Freeze the completed corpus version.

Complete when: The annotation minimum is met and the final audit passes. Attempted records do not count as successfully annotated records.

Evidence: Corpus manifest, audit report, summary tables, and operational logs.

Status: __________
Actual hours: __________
Evidence location: __________

Step 10 — Prepare human reference data

Calibration preparation can begin earlier, after the expert partitions are frozen.

Tasks

- Prepare sentiment, sarcasm, uncertainty, and linguistic-coding guidelines.

- Calibrate both annotators independently.

- Apply the proposal’s individual Kappa criterion of at least 0.61.

- Document calibration rounds and any reused items.

- Freeze the guidelines.

- Sample 500–1,000 target posts using the specified class, route, and author controls.

- Freeze sample IDs before classifier training.

- Provide separate annotation files without machine predictions.

- Preserve original independent annotations.

- Calculate human–human agreement before discussion.

- Resolve disagreements while remaining blind to machine outputs.

- Retain unresolved cases and reasons.

- Complete linguistic coding for both evaluation datasets.

Complete when: Independent annotations, agreement results, final references, and exclusions are documented.

Evidence: Guidelines, calibration report, sample manifest, original annotations, and reconciliation log.

Status: __________
Student coordination hours: __________
Annotator hours: __________
Evidence location: __________

Step 11 — Run the classifier comparison

Training can proceed alongside human annotation once evaluation IDs are frozen.

Tasks

- Freeze the shared RQ2 training pool after evaluation exclusions.

- Create five author folds.

- Exclude all primary gold posts from training.

- Exclude each fold’s test authors from that fold’s training.

- Add only permitted external training data.

- Initialise classifiers from original pretrained checkpoints.

- Apply the proposal’s fixed shared training configuration.

- Complete three models × five folds × three seeds: 45 runs.

- Evaluate the final epoch without test-guided checkpoint selection.

- Save probabilities, predictions, runtime, and truncation rates.

- Prepare primary out-of-fold predictions.

- Prepare secondary predictions using the specified fold-probability averaging.

Complete when: All prescribed runs are accounted for and prediction coverage is verified.

Evidence: Training-pool manifest, fold assignments, 45-run ledger, logs, and prediction files.

Status: __________
Actual hours: __________
Evidence location: __________

Step 12 — Evaluate and interpret results

Tasks

- Report annotation scale separately from annotation quality.

- Compare the framework and individual voters against identical human references.

- Report agreement measures, confusion matrices, and class-specific scores.

- Analyse shared voter errors and majority coverage.

- Count errors corrected and introduced by adjudication.

- Report three-way disagreements separately.

- Calculate RQ2 Macro-F1 and variation across seeds.

- Report primary and secondary evaluation results separately.

- Analyse code-mixing and spelling-noise groups.

- Report subgroup sizes, class coverage, and inconclusive findings.

- Implement the prescribed author-level uncertainty and statistical comparisons.

- Avoid treating stratified-sample results as automatic corpus-wide estimates.

Complete when: Both research questions have results supported by correct denominators, uncertainty, and limitations.

Evidence: Evaluation scripts, result tables, figures, statistical outputs, and error analysis.

Status: __________
Actual hours: __________
Evidence location: __________

Step 13 — Test and package the final system

Tasks

- Test input handling, joins, routing, batching, failures, and recovery.

- Record bugs and recompute affected outputs consistently.

- Reproduce a representative run from saved instructions.

- Prepare preview and testing demonstrations.

- Keep saved outputs available as demonstration backups.

- Write implementation, results, discussion, and limitations.

- Document deviations from FYP 1.

- Package code, configurations, permitted outputs, and reproduction instructions.

- Verify that the report matches the actual implementation.

- Back up the final deliverables.

Complete when: The system is demonstrable, the results are traceable, and another person can follow the reproduction instructions.

Evidence: Test report, reproduction guide, final report, and deliverable manifest.

Status: __________
Actual hours: __________
Evidence location: __________

4. Daily progress log

Record what was achieved, not only what activity was attempted.

| Date | Step | Work completed | Active hours | Evidence or run ID | Next action |
| --- | --- | --- | --- | --- | --- |

5. Experiment record template

Create one record per experiment, or use these fields in a separate experiment ledger.

- Experiment ID:

- Purpose:

- Date and status:

- Code version:

- Dataset and partition versions:

- Model and tokenizer revisions:

- Prompt version, if applicable:

- Training condition, fold, and seed:

- Hyperparameters and precision:

- Hardware and environment:

- Input and evaluation counts:

- Metrics and evaluation dataset:

- Runtime and peak GPU memory:

- Failures and retries:

- Output locations:

- Conclusion and next action:

Preserve failed and unfavourable experiments. Do not document only the best runs.

6. Decision and change log

| Date | Decision | Previous choice | New choice | Reason and evidence | Affected experiments | Supervisor feedback |
| --- | --- | --- | --- | --- | --- | --- |

Record whether final test results had already been viewed when a methodological change was considered.

7. Problem and resolution log

| Date | Problem | Affected step | Cause or hypothesis | Action taken | Verification | Status |
| --- | --- | --- | --- | --- | --- | --- |

8. Supervisor meeting log

| Date | Progress demonstrated | Feedback | Agreed actions | Due date | Completion evidence |
| --- | --- | --- | --- | --- | --- |

9. Time and computing-cost log

Keep student working hours, annotator hours, GPU processing hours, and billed cloud hours separate.

| Date | Job | Hardware | Active GPU hours | Billed hours | Cost and currency | Output location |
| --- | --- | --- | --- | --- | --- | --- |

10. Weekly review

Week ending: __________

- Milestones completed:

- Evidence produced:

- Student working hours:

- Annotator progress:

- GPU usage and expenditure:

- Remaining workload:

- Current blockers:

- Supervisor decisions needed:

- Next week’s three priorities:

- Schedule changes and reasons:

11. Documentation habits

- Update the progress log after each work session.

- Save configuration and output locations for every experiment.

- Record decisions when they happen.

- Keep original annotations and raw datasets unchanged.

- Link to detailed evidence instead of pasting large logs into this document.

- Review milestone progress weekly.

- Use actual achieved counts and measured runtimes in the final report.