## Stage Tracker
FYP implementation tracker
Methodology aligned: 26 October 2026. Recorded progress: 24 October 2026; Stages 1.1–1.4 complete. Final A/B/C freeze remains in 1.5.
Substages | 34 | Complete | 4 | In progress | 0 | Update Status and Next action as work progresses. Completion requires the stated criterion.
Stage | Main stage | Activity | Status | Dependencies | Expected outputs | Completion criterion | Next action / current evidence | Document section
1.1 | Prepare Voter 1 training data | MESocSentiment: Candidate A | Complete | Source MESoc files | Candidate A CSV; exclusion and duplicate logs; suspicious-text reports; script; manifest | Preparation is reproducible and local quality decisions are recorded; final cross-dataset freeze occurs in 1.5. | User reports preparation complete. Final cross-dataset freeze and outstanding quality review remain in Stage 1.5. | 3.3.2
1.2 | Prepare Voter 1 training data | Prepare and partition the expert corpus | Complete | Expert source files; decision D05 | Training (800), development (600), calibration (120) and secondary test (761) CSVs; partition manifest | Validate the expected 2,281 labelled code-mixed posts; record seed, labels, IDs, author separation and immutable membership. | Verified 2,281 posts; 1,951 authors; 800/600/120/761; seed 42. No author, ID or exact-text overlap. Fixed v1 membership saved. | 3.6.1; 3.7.2
1.3 | Prepare Voter 1 training data | Expert-only: Candidate B | Complete | 1.2; decision D06 | Candidate B CSV; inclusion rules; manifest | Only permitted expert training rows included; protected partitions excluded. | Verified 800 posts / 684 authors; source-identical CSV; zero protected ID, author or exact-text overlap. Final freeze: Stage 1.5. | 3.3.2; 3.6.1
1.4 | Prepare Voter 1 training data | Combined: Candidate C | Complete | 1.1; 1.3 | Candidate C CSV; cross-source duplicate log; neutral-sampling log | Combine permitted A/B rows; apply a documented neutral subsampling rule with fixed seed. | Verified 7,430 rows: 1,368 negative, 3,031 neutral, 3,031 positive. All 800 expert rows retained; seed 42. Eight output files reproduced byte for byte; 4 tests passed. Final freeze: Stage 1.5. | 3.3.2
1.5 | Prepare Voter 1 training data | Check separation and freeze A/B/C | Planned | 1.1–1.4; 2.1 | Overlap report; tokenizer-length report; frozen manifests; shared training configuration | Resolve protected ID/text overlaps; check author separation where IDs exist. Review flagged text, document tokenizer truncation and quality decisions, and hash final A/B/C inputs. | Complete hardware/tokenizer checks first. Review 1,400 flagged A candidates; record MESoc author-ID limitations. Apply any final exclusions consistently to derived candidates. | 3.3.2; 3.6.1; 3.8
2.1 | Train and select Voter 1 | Set up environment and model versions | Planned | Start early, before 1.5 | Environment specification; model/tokenizer revisions; memory and timing checks | Verify the intended workstation supports the pinned precision, quantisation and attention settings. Record actual hardware, memory and software versions. | Test the XLM-R tokenizer/configuration before 1.5. Check decoder/adjudicator memory feasibility early; record compatible settings for the 8 GB GPU. | 3.8.1–3.8.3
2.2 | Train and select Voter 1 | Implement shared training pipeline | Planned | 1.5; 2.1; decision D09 | Training/evaluation script; checkpoint and run-log schema | Use identical hyperparameters and evaluation rules across A/B/C; fix three seeds, condition tie handling and the operational checkpoint rule before inspecting comparison results. | Record D09; validate a short training run and checkpoint reload. Keep development scoring separate from protected calibration/test data. | 3.3.2
2.3 | Train and select Voter 1 | Compare A/B/C under three seeds | Planned | 2.2; D09 recorded | Nine run results; Macro-F1 summary; per-class results | Complete three seeds per condition and compare mean Macro-F1 on permitted expert development data. | Run three seeds per condition; compare mean Macro-F1 on the 600-post expert development set. Save per-class metrics and predicted-class distributions. | 3.3.2
2.4 | Train and select Voter 1 | Select and freeze Voter 1 | Planned | 2.3; decision D09 | Selected checkpoint; selection report; predicted-class distribution | Choose the condition by mean development Macro-F1; apply the prespecified tie/checkpoint rule and freeze the operational model before target annotation. | Inspect neutral bias on development data; pin weights, tokenizer, preprocessing and revision. Never use gold or secondary-test performance for selection. | 3.3.2; 3.6.1
3.1 | Prepare the target corpus | Inventory target source and assign IDs | Planned | Raw Maskat target corpus | Tier 1 inventory; stable post IDs; author mapping; provisional five-fold plan | Assign stable IDs on first read; preserve author/source mapping. Plan five folds of ten authors before sampling, and check eligible author coverage after filtering. | Hash raw sources and retain author IDs. Prepare author coverage for 6.2 and 7.1; finalise eligible fold records after gold creation. | 3.2.1–3.2.3
3.2 | Prepare the target corpus | Filter and lightly clean target text | Planned | 3.1 | Filtered target CSV; exclusion log; preprocessing configuration | Document duplicate, length and spam rules and URL/mention handling; preserve sentiment-bearing text features. | Implement filters with exclusion reasons and before/after counts. | 3.2.3–3.2.4
3.3 | Prepare the target corpus | Specify linguistic coding protocol | Planned | Revised document 3.7.3; 1.2 | Draft token guide; CMI = min(M,E)/(M+E); noise rate = flagged lexical tokens / resolved lexical tokens | Plan human coding of evaluation posts after sampling. Linguistic bands are analysis groups, not sampling strata or corpus filters; freeze the guide in 6.1. | Code-mixing: zero; 0 < score < 0.20; 0.20–0.50. Noise: zero; 0 < rate <= 0.10; > 0.10. Follow token exclusions in 3.7.3; do not assume source token-language labels exist. | 3.2.3; 3.6.2; 3.7.3
3.4 | Prepare the target corpus | Validate and freeze annotation input | Planned | 3.1; 3.2 | Annotation-input manifest; quality and author-coverage report | Verify stable IDs, counts, deduplication, author coverage and preserved sentiment features; freeze the machine-annotation inputs. Human linguistic coding is not a prerequisite. | Reconcile exclusions and eligible authors. Resolve any missing-author coverage before the production sampling and fold design are fixed. | 3.2; 3.8
4.1 | Build and validate the framework | Implement three voter inference paths | Planned | 2.4; 2.1 | XLM-R, Llama 3.1 8B and Qwen2.5 7B inference scripts; fixed prompt | Return valid three-class predictions; generative voters use the same fixed instruction and constrained output. | Pin releases and test sequential model loading. | 3.3.2–3.3.3
4.2 | Build and validate the framework | Extract and cache confidence | Planned | 4.1 | Full three-class probabilities; labels; IDs; model/prompt/configuration versions | Verify generative label tokenisation in the actual prompt context, normalisation and label mapping; retain every voter's full distribution and prediction for each post. | Check finite probabilities summing to one and consistent argmax labels. Do not substitute verbal self-reported confidence for model probabilities. | 3.4.2
4.3 | Build and validate the framework | Implement confidence gate | Planned | 4.2 | Routing script; branch checks; threshold schema; initial-majority records | Accept only if at least two agreeing voters each meet their own threshold. Route every other case, including weak unanimity; record three-way ties as initially unresolved. | Test all Table 3.6 branches and threshold boundaries. Retain majority label, route and reason; a three-way tie is never automatically neutral. | 3.4.3
4.4 | Build and validate the framework | Implement the adjudicator | Planned | 4.3 | SEA-LION adjudication script; prompt; retry and output logs | Use the specified Gemma 2 lineage; supply text and anonymous votes; runtime failures are retried. | Pin the exact release and test the local memory configuration. | 3.5.1–3.5.2
4.5 | Build and validate the framework | Validate on expert development data | Planned | 1.2; 4.1–4.4 | Tuned thresholds; development diagnostics; frozen configuration and sensitivity plan | Tune and trial only on the 600-post development set. Check voter bias, shared errors and route-specific adjudication gains/losses; freeze all choices before final evaluation. | Record the threshold search and selection objective, adjudicator/prompt changes, and sensitivity settings (including the stricter rule). No tuning on gold or expert secondary test. | 3.6.1
4.6 | Build and validate the framework | Verify long-run readiness | Planned | 4.4; 4.5 | Resumable runner; shard/ID checks; availability configuration; recovery test | Recover after interruption without missing/duplicate IDs; flush and release GPU before booked periods. | Perform an interruption-and-resume check before production. | 3.8.2
5.1 | Produce the annotated corpus | Run throughput pilot | Planned | 3.4; 4.5; 4.6 | 5,000–10,000-post pilot; per-stage runtime, memory and route report | Measure all voters, gate and adjudicator; record loading, retries and routed share. Project runtime using observed throughput and available workstation time. | Use representative target posts and the frozen pipeline. Record active processing time separately from booked-machine interruptions. | 3.1.2; 3.8.1
5.2 | Produce the annotated corpus | Fix production run size | Planned | 5.1 | Production scope; selected IDs; author coverage; measured compute estimate | Fix a feasible production scope of at least 150,000 posts. Preserve eligible author coverage for gold sampling and five-fold evaluation; record subset selection and seed. | Use pilot timing and actual availability. Distinguish RQ1 annotation scale from the separately fixed RQ2 target training pool in 7.1. | 3.1.2
5.3 | Produce the annotated corpus | Annotate the target corpus | Planned | 5.2 | Tier 2 labels; probabilities; initial votes/majorities; route/adjudication logs; timing | Every included post receives a valid final label; cache traceable voter outputs, routes and adjudication results. Recover from interruptions and retry runtime failures. | Run all voters, gate and adjudicator; retry failures. | 3.3–3.5; 3.8.2
5.4 | Produce the annotated corpus | Audit Tier 2 outputs | Planned | 5.3 | Tier 2 manifest; ID/route reconciliation; initial/final label distributions | No missing/duplicate IDs, invalid labels or unresolved runtime failures. Reconcile route totals and initial-to-final transitions; retain initial three-way ties as unresolved. | Report final corpus size, author coverage and class counts. Distribution changes alone do not establish better annotation quality. | 3.8.2–3.8.3
6.1 | Human validation and RQ1 | Calibrate annotators and coding guide | Planned | 1.2; 3.3; D10; recruit early | Guidelines; independent calibration labels; per-annotator results; frozen linguistic guide | Two daily Manglish-using native bilingual Malaysian annotators each achieve Cohen's kappa >= 0.61 against the expert calibration reference before final annotation. | Use the reserved 120 posts; blind expert labels. Report raw agreement/AC1 as supplements. Log repeat rounds and reuse; freeze sentiment, sarcasm, uncertainty and linguistic coding rules. | 3.6.2; 3.7.3
6.2 | Human validation and RQ1 | Select the gold sample | Planned | 5.4; author plan from 3.1 | 500–1,000 sampled IDs; strata sizes; inclusion probabilities; seed; author coverage | Stratify by predicted sentiment and routing branch; oversample minority predictions/adjudicated cases. Apply an author cap and cover all 50 authors where eligible. | Fix allocation before human labels. Record selection probabilities including author controls. Do not stratify by code-mixing/noise; assign these groups after sampling. | 3.6.2–3.6.3
6.3 | Human validation and RQ1 | Collect blinded labels and linguistic codes | Planned | 6.1; 6.2; 1.2 secondary test | Independent target sentiment/sarcasm/uncertainty files; linguistic codes for both test sets | Two annotators work independently, blind to machine labels and classifier predictions. Retain original labels, difficult/uncertain flags and reasons. | Code Malay/English tokens and spelling noise on target gold and expert secondary posts using the frozen guide; log unresolved tokens, standard forms and reasons. | 3.6.2; 3.7.3
6.4 | Human validation and RQ1 | Finalise gold references and analysis groups | Planned | 6.3 | Pre-discussion agreement; consensus reference; unresolved log; linguistic group manifests | Calculate human-human agreement before discussion. Resolve labels/codes blind to machine predictions; retain unresolved cases without forcing a three-class sentiment. | Report kappa, raw agreement, AC1 and coding agreement. State eligible denominators and exclusions; uncertain flags alone do not exclude valid independent labels. | 3.6.2; 3.7.3
6.5 | Human validation and RQ1 | Evaluate H1 and annotation components | Planned | 6.4; 5.4; 4.5 frozen; D07 | Both test-source results; paired baseline differences; voter/routing analysis; transition and adjudication tables | On the same eligible human-reference posts, score framework and each voter separately for gold and expert secondary test. Report kappa, raw agreement, AC1, confusion matrices and per-class scores. Quantify shared errors and voting-pattern accuracy overall and for negative, sarcasm, high-mixing and high-noise groups. | Use 2,000 paired author bootstraps, seed 42, for 95% intervals. Compare pre/post adjudication on all majority-covered posts and their routed subset; report errors corrected/introduced, route metrics and transitions. Report three-way tie coverage/accuracy separately. Keep unweighted results sample-level; population weighting needs defensible inclusion probabilities. See D07 and 3.6.2. | 3.6.2–3.6.4
6.6 | Human validation and RQ1 | Report prespecified routing sensitivity | Planned | 6.5; sensitivity plan frozen in 4.5 | Threshold/rule comparisons; changed-route results; quality and compute differences | Apply prespecified comparisons, including the stricter rule, using cached probabilities. Adjudicate newly routed posts as needed; keep primary configuration fixed. | Report sensitivity separately from primary results; never select thresholds/rules from final test scores. Record runtime and added adjudication cost. | 3.4.3; 3.8.3
7.1 | RQ2 experiments and release | Freeze RQ2 pool and author folds | Planned | 1.2; 5.4; 6.4; 3.1 author plan; D05/D08 | Fixed target-pool IDs; five author-fold manifests; eligible external training files; overlap report | Select 150,000 eligible machine-labelled posts (or all if fewer), seed 42, proportionally by author. Exclude all primary gold posts globally and all held-out authors within each fold. | Add permitted Malay-only, English-only and code-mixed expert training rows identically to all models. Exclude development/calibration/secondary-test authors and evaluation overlaps; freeze source counts. | 3.6.1; 3.7.1–3.7.2
7.2 | RQ2 experiments and release | Run the 45 fixed RQ2 training jobs | Planned | 7.1; 2.1; D08 | 45 checkpoints/run logs; shared configuration; per-model timing and truncation report | Three models x five author folds x seeds 42/123/2024. Start from original pretrained checkpoints; identical permitted data; three epochs, final-epoch checkpoint; no hyperparameter search. | Use D08 settings. Time an initial representative job for each model before full scheduling; revise compute allowance from measured throughput without using test results. | 3.7.1; 3.8.1
7.3 | RQ2 experiments and release | Score both tests and paired comparisons | Planned | 7.2; 6.4; D08 | Per-seed pooled primary metrics; secondary ensemble metrics; paired intervals and adjusted tests | Primary: pool held-out-author predictions once per post per seed. Secondary: average probabilities over five fold models within each seed, then score; report sources separately. | Report Macro-F1 mean/SD across seeds, per-class scores, confusion matrices and fold/author variation. Use 2,000 author-bootstrap replicates and 10,000 paired author permutations, seed 42; Holm-adjust the two primary p-values at 0.05. Folds are not independent replicates. | 3.7.2–3.7.3
7.4 | RQ2 experiments and release | Analyse robustness and failures | Planned | 7.3; 6.4 linguistic groups | Mixing/noise subgroup scores; signed contrasts and intervals; author/sarcasm error analysis | Apply the frozen human-coded groups to both tests. Report post/author/class counts, per-class scores and paired author-bootstrap intervals; assess H2 components separately. | Compare XLM-R minus each baseline and high-minus-low group contrasts. Groups <30 posts or missing a class are descriptive only; flag intervals if <95% bootstrap replicates are valid. | 3.7.3
7.5 | RQ2 experiments and release | Package evidence and write results | Planned | 6.5; 6.6; 7.4 | Scripts/configs; label-ID release; probability/routing records; result tables; written chapters | Publish reproducible prompts, thresholds, model revisions, seeds, data manifests and result methods. Preserve source acknowledgements and label-ID mapping without redistributing source text. | Include sampling limits, unresolved cases, author/domain and label-provenance limits, per-stage compute cost and unfavourable/inconclusive results. Align the document overview with final evaluation coding. | 3.8.2–3.9

## Output Register
Output register
Existing files only. Expected future deliverables are listed in Stage Tracker; add actual files here when created.
Snapshot only: file links open the current file; row counts and verification notes do not refresh automatically.
Stage | Output file | Purpose | Artifact state | Records (CSV) | Version | Absolute location | Verification / remaining limitation
1.1 | condition_a_training.csv | Candidate A input; not frozen for training | Candidate | 16968 | v1 (current) | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.1 - MESoc Preparation (Candidate A)/MESocSentiment_Condition_A_v1/condition_a_training.csv | Verified in preparation audit; training freeze pending
1.1 | mesoc_exclusions.csv | Recoverable excluded rows and reasons | Created | 2746 | v1 (current) | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.1 - MESoc Preparation (Candidate A)/MESocSentiment_Condition_A_v1/mesoc_exclusions.csv | Verified in preparation audit; training freeze pending
1.1 | mesoc_reserved_test.csv | Supplied test examples; retain automatic/manual labels | Created | 2000 | v1 (current) | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.1 - MESoc Preparation (Candidate A)/MESocSentiment_Condition_A_v1/mesoc_reserved_test.csv | Verified in preparation audit; training freeze pending
1.1 | mesoc_duplicate_review.csv | Original flagged pairs and applied policy decisions | Created | 582 | v1 (current) | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.1 - MESoc Preparation (Candidate A)/MESocSentiment_Condition_A_v1/mesoc_duplicate_review.csv | Verified in preparation audit; training freeze pending
1.1 | mesoc_suspicious_text.csv | Flagged source records with candidate/excluded disposition | Created | 1410 | v1 (current) | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.1 - MESoc Preparation (Candidate A)/MESocSentiment_Condition_A_v1/mesoc_suspicious_text.csv | Verified in preparation audit; training freeze pending
1.1 | suspicious_text_summary.json | Scan thresholds, rules and aggregated counts | Created |  | v1 (current) | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.1 - MESoc Preparation (Candidate A)/MESocSentiment_Condition_A_v1/suspicious_text_summary.json | Verified in preparation audit; training freeze pending
1.1 | preparation_manifest.json | Source/script hashes, processing rules and counts | Created |  | v1 (current) | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.1 - MESoc Preparation (Candidate A)/MESocSentiment_Condition_A_v1/preparation_manifest.json | Verified in preparation audit; training freeze pending
1.1 | Preparation_Report.md | Human-readable preparation decisions and instructions | Created |  | v1 (current) | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.1 - MESoc Preparation (Candidate A)/MESocSentiment_Condition_A_v1/Preparation_Report.md | Verified in preparation audit; training freeze pending
1.1 | prepare_mesoc.py | Reproduce preparation, exclusions and suspicious-text scanning | Created |  | v1 (current) | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.1 - MESoc Preparation (Candidate A)/MESocSentiment_Condition_A_v1/prepare_mesoc.py | Verified in preparation audit; training freeze pending
1.1 | prepare_mesoc.py (stage copy) | Same processor at the stage-folder level | Created |  | Matches package copy | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.1 - MESoc Preparation (Candidate A)/prepare_mesoc.py | Both script copies verified identical
1.2 | expert_training.csv | Permitted Candidate B input | Created | 800 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.2 - Prepare and partition the expert corpus/expert_partitions_v1/expert_training.csv | 684 authors; negative 346, neutral 225, positive 229.
1.2 | expert_development.csv | Development and tuning | Created | 600 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.2 - Prepare and partition the expert corpus/expert_partitions_v1/expert_development.csv | 514 authors; negative 260, neutral 168, positive 172.
1.2 | expert_calibration.csv | Human annotator calibration | Created | 120 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.2 - Prepare and partition the expert corpus/expert_partitions_v1/expert_calibration.csv | 105 authors; negative 52, neutral 34, positive 34.
1.2 | expert_secondary_test.csv | Protected secondary test | Created | 761 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.2 - Prepare and partition the expert corpus/expert_partitions_v1/expert_secondary_test.csv | 648 authors; negative 330, neutral 213, positive 218.
1.2 | partition_membership.csv | Fixed post-to-author partition assignments | Created | 2281 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.2 - Prepare and partition the expert corpus/expert_partitions_v1/partition_membership.csv | All eligible IDs assigned once; pairwise author/ID/exact-text disjoint.
1.2 | partition_manifest.json | Seed, rules, class counts and file hashes | Created |  | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.2 - Prepare and partition the expert corpus/expert_partitions_v1/partition_manifest.json | Seed 42; all checks passed; cross-dataset checks remain for 1.5.
1.2 | excluded_records.csv | Excluded source records and reasons | Created | 7719 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.2 - Prepare and partition the expert corpus/expert_partitions_v1/excluded_records.csv | 7,680 non-code-mixed; 39 code-mixed without valid sentiment.
1.2 | duplicate_text_review.csv | Retained repeated-text records | Created | 2 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.2 - Prepare and partition the expert corpus/expert_partitions_v1/duplicate_text_review.csv | IDs 39303 and 37432 retained together in training; near-duplicates not audited.
1.2 | Partition_Report.md | Partition results and limitations | Created |  | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.2 - Prepare and partition the expert corpus/expert_partitions_v1/Partition_Report.md | Original five columns preserved; source unchanged.
1.2 | partition_expert.py | Reproduce fixed author-disjoint partitions | Created |  | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.2 - Prepare and partition the expert corpus/partition_expert.py | Refuses existing output directory; use same source and seed.
1.2 | analyze_authors.py | Reproduce author and data-quality audit | Created |  | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.2 - Prepare and partition the expert corpus/analyze_authors.py | Counts authors and posts; no source edits.
1.3 | condition_b_training.csv | Expert-only Candidate B input | Candidate | 800 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.3 - Expert-only Preparation (Candidate B)/Expert_Condition_B_v1/condition_b_training.csv | 800 posts; 684 authors; 346 negative, 225 neutral, 229 positive.
1.3 | preparation_manifest.json | Provenance, rules, counts and hashes | Created |  | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.3 - Expert-only Preparation (Candidate B)/Expert_Condition_B_v1/preparation_manifest.json | Input hashes match Stage 1.2; output is byte-identical to training source.
1.3 | validation_report.json | Membership and protected-partition checks | Created |  | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.3 - Expert-only Preparation (Candidate B)/Expert_Condition_B_v1/validation_report.json | All checks passed; zero ID, author and exact-text overlap with protected partitions.
1.3 | Preparation_Report.md | Inclusion rules and reproduction guidance | Created |  | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.3 - Expert-only Preparation (Candidate B)/Expert_Condition_B_v1/Preparation_Report.md | Original text and membership retained; final freeze remains in Stage 1.5.
1.3 | prepare_candidate_b.py | Reproduce Candidate B preparation | Created |  | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.3 - Expert-only Preparation (Candidate B)/prepare_candidate_b.py | Standard-library Python; validates source hashes; refuses existing output directory.
1.4 | condition_c_training.csv | Combined Candidate C training input | Candidate | 7430 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.4 - Combined Preparation (Candidate C)/Combined_Condition_C_v1/condition_c_training.csv | 1,368 negative; 3,031 neutral; 3,031 positive. All 800 expert rows retained. Freeze pending.
1.4 | cross_source_duplicate_log.csv | Exact A/B duplicate decisions | Created | 0 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.4 - Combined Preparation (Candidate C)/Combined_Condition_C_v1/cross_source_duplicate_log.csv | No exact trimmed-text A/B pairs. Header-only log; expert B takes precedence.
1.4 | near_duplicate_review.csv | Cross-source heuristic duplicate flags | Created | 0 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.4 - Combined Preparation (Candidate C)/Combined_Condition_C_v1/near_duplicate_review.csv | No flags from documented heuristic; scan is not exhaustive. Review remains in 1.5.
1.4 | neutral_sampling_log.csv | Deterministic neutral selection audit | Created | 13144 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.4 - Combined Preparation (Candidate C)/Combined_Condition_C_v1/neutral_sampling_log.csv | 2,806 selected from 13,144 A neutral rows. Seed 42; SHA-256 ranks recorded.
1.4 | row_inclusion_log.csv | Disposition of every input row | Created | 17768 | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.4 - Combined Preparation (Candidate C)/Combined_Condition_C_v1/row_inclusion_log.csv | 7,430 retained; 10,338 A neutral rows excluded. Inputs preserved.
1.4 | validation_report.json | Membership, class and protected-overlap checks | Created |  | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.4 - Combined Preparation (Candidate C)/Combined_Condition_C_v1/validation_report.json | All checks passed. B internal repeated-text IDs retained. MESoc author IDs unavailable.
1.4 | preparation_manifest.json | Input/script/output checksums and counts | Created |  | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.4 - Combined Preparation (Candidate C)/Combined_Condition_C_v1/preparation_manifest.json | Locked input hashes; deterministic output hashes. Final freeze pending Stage 1.5.
1.4 | Preparation_Report.md | Rules, limitations and reproduction instructions | Created |  | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.4 - Combined Preparation (Candidate C)/Combined_Condition_C_v1/Preparation_Report.md | Python 3.9+ standard library; target rule, seed and sampling algorithm documented.
1.4 | prepare_candidate_c.py | Reproduce Candidate C and audit files | Created |  | v1 | C:/Users/Lenovo/Desktop/Sentiment Analysis FYP/RQ1/Stage 1.4 - Combined Preparation (Candidate C)/prepare_candidate_c.py | Verifies input hashes; refuses existing output directories; preserves source files.

## Decision Log
Decision log
Methodology aligned on 26 October 2026. Earlier preparation decisions remain recorded; unresolved implementation choices remain Open.
Source | FYP 1 (Done revising).docx |  | Basis: revised Chapter 3, reviewed 26 October 2026. Historical preparation evidence dated 24 October 2026. No deadlines assumed.
ID | Affected stages | Status | Decision topic | Recorded outcome / editable decision | Reason or constraint | Required follow-up | Source / basis
D01 | 1.1 | Recorded | Near-duplicate exclusion | Exclude every candidate endpoint in the original flagged pairs; preserve reserved records. | User chose automatic discarding; 582 pairs led to 746 unique candidate exclusions. | Applied; retain recoverable rows in the exclusion log. | Conversation decision; preparation_manifest.json
D02 | 1.1 | Recorded | Suspicious-text policy | Flag only; do not automatically delete or alter suspicious text. | Short posts, emoji and Manglish spelling may still carry valid sentiment. | Assess the 1,400 flagged remaining candidates before final freeze. | Implemented scan policy; suspicious_text_summary.json
D03 | 1.1 | Recorded | Preserve folder structure | Keep current folders and filenames; root argument points to RQ1. | User requested the existing structure be retained. | Use the reproduction example in Preparation_Report.md. | User request; preparation report
D04 | 1.1 | Recorded | Reserve supplied test matches | Exclude exact trimmed-text test matches from training. | 2,000 corpus rows are reserved; this is not the expert development set. | Preserve reserved data and record exclusions. | Preparation manifest; Portfolio 3.3.2
D05 | 1.2; 7.1 | Recorded | Expert partition constraints | Achieved v1 allocation: 800 training / 600 development / 120 calibration / 761 secondary test; author-disjoint; seed 42. Preserve frozen membership. | The document sets approximate targets and prioritises author separation. The recorded v1 allocation meets the targets; exact counts are an achieved result, not a reason to weaken separation. | Keep v1 membership. Exclude development/calibration/test authors from all expert training portions, including Malay-only and English-only data prepared for RQ2. | Revised document 3.6.1; partition_manifest.json; recorded verification, 24 October 2026
D06 | 1.3 | Recorded | Candidate B eligible expert rows | Candidate B uses only the 800 labelled code-mixed training posts. No monolingual data. | Historical Stage 1.3 restriction applies to Candidate B. RQ2 separately includes eligible Malay-only and English-only expert data under 3.7.2. | Keep Candidate B at 800 code-mixed posts. Prepare permitted external RQ2 portions separately in 7.1; protect all reserved authors. | User decision, 24 October 2026; expert_training.csv
D07 | 6.5 | Superseded | Two-decoder baseline ties | No required two-decoder baseline in the revised method. H1 compares the framework against XLM-R, Llama and Qwen individually, using their cached pre-routing labels. | The revised H1 baseline specification replaces the old tie-handling task. Support for H1 requires positive evidence against all three individual voters; mixed results must be named. | Report framework-minus-voter kappa differences with 2,000 paired author-bootstrap replicates, seed 42. Mark intervals unreliable if <95% are valid; retain three-way majority ties as unresolved in component analysis. | Revised document 3.6.2; Table 3.14
D08 | 7.1–7.3 | Recorded | Fixed RQ2 training and scoring protocol | 45 runs: 3 models x 5 author folds x seeds 42, 123, 2024. Target pool: 150,000 eligible posts or all if fewer; seed 42, proportional author allocation. No hyperparameter search. | Shared settings: AdamW, learning rate 2e-5, weight decay 0.01, linear schedule, 10% warm-up, effective batch 16, max length 128 model-specific tokens, unweighted cross-entropy, no class resampling, 3 epochs; use final checkpoint. | Pin FacebookAI/xlm-roberta-base, google-bert/bert-base-uncased and indobenchmark/indobert-base-p1. Pool primary out-of-fold predictions per seed; average 5-fold probabilities for secondary scoring. Measure run times before scheduling all jobs. | Revised document 3.7.1–3.7.3; Table 3.14
D09 | 2.2–2.4 | Open | Operational Voter 1 checkpoint |  | Condition selection by mean development Macro-F1 is fixed. The operational checkpoint rule and condition-tie handling still require a recorded implementation decision. | Prespecify and record the rule before inspecting A/B/C comparison results. Apply it in 2.4; do not use calibration, secondary-test or gold labels for selection. | Revised document 3.3.2; implementation decision still open
D10 | 6.1 | Recorded | Annotator calibration pass criterion | Each annotator independently achieves unweighted Cohen's kappa >= 0.61 against the expert reference on the reserved calibration portion before evaluation annotation. | Raw percentage agreement, Gwet's AC1 and class distributions are supplementary. The 0.61 threshold applies only to each annotator's kappa, not to those measures or framework performance. | Blind expert labels and other responses. Log all rounds and reused posts; reviewed-item performance shows training progress. Freeze sentiment and linguistic guides before final coding. | Revised document 3.6.2; 3.7.3
D11 | 1.4 | Recorded | Combined-condition neutral sampling | Keep all expert and eligible non-neutral rows. Neutral total = larger positive/negative class. Select A neutral rows by seed-42 SHA-256 ranking. Exact cross-source text matches: retain expert B; exclude A. | User approved reducing neutral dominance while preserving all 800 expert examples. A and B remain unchanged. | Applied: 2,806 A neutral + 225 B neutral = 3,031. No exact cross-source pairs found. Preserve prior within-source decisions; final review/freeze in 1.5. | User decision, 24 October 2026; Candidate C preparation manifest and reproducibility verification.